## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
SPRINT 6
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION (In Days) | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Requirements Analysis |  | 20 | 20 | 0 |  |  |  | 5 | 100%
1.1 | Get all research articles relevant to the project | Smeet | 2 | 2 | 0 | 1 | 2025-03-03 | 2025-03-03 | 1 | 100% | bar: WEEK 1 M
1.2 | Study and Deep dive in all the articles | Smeet & Nilesh | 10 | 10 | 0 | 1 | 2025-03-04 | 2025-03-05 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
1.3 | Data set gathering | Nilesh | 3 | 3 | 0 | 1 | 2025-03-06 | 2025-03-06 | 1 | 100% | bar: WEEK 1 T
1.4 | Data cleaning | Nilesh | 5 | 5 | 0 | 1 | 2025-03-07 | 2025-03-07 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
2 | Data Analysis |  | 24 | 24 | 0 |  |  |  | 8 | 100%
2.1 | Exploratory Data Analysis | Smeet | 15 | 15 | 0 | 1 | 2025-03-10 | 2025-03-14 | 5 | 100%
2.2 | Visualization and Feature Correlation | Smeet | 3 | 3 | 0 | 2 | 2025-03-17 | 2025-03-17 | 1 | 100% | bar: WEEK 2 M to WEEK 3 M
2.3 | Label Encoding | Nilesh | 2 | 2 | 0 | 2 | 2025-03-18 | 2025-03-18 | 1 | 100% | bar: WEEK 3 T
2.4 | Implement feature engineering pipeline (time-based features) | Nilesh | 4 | 4 | 0 | 2 | 2025-03-19 | 2025-03-19 | 1 | 100% | bar: WEEK 3 W
3 | Machine learning models Implementation and Testing |  | 64 | 64 | 0 |  |  |  | 23 | 100%
3.1 | Implement Linear Regression as a baseline model | Nilesh | 15 | 15 | 0 | 2 | 2025-03-20 | 2025-03-28 | 7 | 100% | bar: WEEK 3 T to WEEK 5 F
3.2 | Create basic Flask API structure with a /predict endpoint | Nilesh | 13 | 13 | 0 | 2 | 2025-03-31 | 2025-04-03 | 4 | 100%
3.3 | Random Forests Implementation | Nilesh | 13 | 13 | 0 | 3 | 2025-04-04 | 2025-04-09 | 4 | 100% | bar: WEEK 5 M to WEEK 6 W
3.4 | Gradient Boosting | Smeet | 17 | 17 | 0 | 3 | 2025-04-10 | 2025-04-17 | 6 | 100% | bar: WEEK 6 T to WEEK 7 T
3.5 | XGBoost Regressor Model Implementation | Smeet | 6 | 6 | 0 | 3 | 2025-04-18 | 2025-04-21 | 2 | 100% | bar: WEEK 7 F to WEEK 8 F
4 | Front end and Web server Building |  | 27 | 27 | 0 |  |  |  | 15 | 100%
4.1 | Build a module to save all the pre trained models | Nilesh | 6 | 6 | 0 | 4 | 2025-04-22 | 2025-04-25 | 4 | 100%
4.2 | Develop HTML pages for the web pages | Smeet | 13 | 13 | 0 | 4 | 2025-04-28 | 2025-05-02 | 5 | 100% | bar: WEEK 8 M to WEEK 9 F
4.3 | Develop and add style sheets for the web page | Smeet | 5 | 5 | 0 | 5 | 2025-05-05 | 2025-05-07 | 3 | 100% | bar: WEEK 8 W to WEEK 8 F; WEEK 10 M to WEEK 10 W
4.4 | Integrate the best-performing model into the Flask API | Nilesh | 3 | 3 | 0 | 5 | 2025-05-08 | 2025-05-12 | 3 | 100% | bar: WEEK 8 M; WEEK 8 W to WEEK 8 F; WEEK 10 T to WEEK 11 F
5 | Deployment,Testing and Analysis |  | 34 | 34 | 0 |  |  |  | 19 | 100%
5.1 | Create a docker-compose.yml file and test local deployment | Smeet | 8 | 8 | 0 | 6 | 2025-05-13 | 2025-05-14 | 2 | 100%
5.2 | Deploy the web app on AWS cloud and run it. | Nilesh | 7 | 7 | 0 | 6 | 2025-05-15 | 2025-05-19 | 3 | 100% | bar: WEEK 8 T to WEEK 8 F; WEEK 11 W to WEEK 12 M
5.3 | Perform end-to-end system testing | Nilesh | 19 | 19 | 0 | 6 | 2025-05-20 | 2025-05-23 | 4 | 100% | bar: WEEK 11 W to WEEK 11 F; WEEK 12 T to WEEK 12 F
5.4 | Finalize project documentation and user manual | Smeet & Nilesh | 19 | 19 | 0 | 6 | 2025-05-20 | 2025-05-23 | 4 | 100% | bar: WEEK 11 W to WEEK 11 F; WEEK 12 T to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked on multiple tasks on a day, we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 169 | 169 | 0 | 70 | 2.4143 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 169 | 169 | 169 | 169 | 167 | 164 | 162 | 159 | 157 | 155 | 152 | 150 | 147 | 145 | 142 | 140 | 138 | 135 | 133 | 130 | 128 | 126 | 123 | 121 | 118 | 116 | 113 | 111 | 109 | 106 | 104 | 101 | 99 | 97 | 94 | 92 | 89 | 87 | 85 | 82 | 80 | 77 | 75 | 72 | 70 | 68 | 65 | 63 | 60 | 58 | 56 | 53 | 51 | 48 | 46 | 43 | 41 | 39 | 36 | 34
[10 empty] | ESTIMATE | 169 | 167 | 162 | 157 | 154 | 149 | 146 | 143 | 140 | 137 | 134 | 132 | 129 | 127 | 123 | 120 | 118 | 118 | 115 | 115 | 112 | 107 | 104 | 103 | 97 | 94 | 89 | 89 | 87 | 82 | 80 | 76 | 71 | 70 | 65 | 63 | 59 | 56 | 53 | 53 | 49 | 47 | 44 | 42 | 38 | 33 | 33 | 27 | 26 | 23 | 18 | 16 | 14 | 12 | 9 | 4 | 0 | 0 | -4 | -10 | 4786
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 2 | 5 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 4 | 3 | 2 | 0 | 3 | 0 | 3 | 5 | 3 | 1 | 6 | 3 | 5 | 0 | 2 | 5 | 2 | 4 | 5 | 1 | 5 | 2 | 4 | 3 | 3 | 0 | 4 | 2 | 3 | 2 | 4 | 5 | 0 | 6 | 1 | 3 | 5 | 2 | 2 | 2 | 3 | 5 | 4 | 0 | 4 | 6 | 2 | 181
[10 empty] | HRS REMAINING | 167 | 162 | 157 | 154 | 149 | 146 | 143 | 140 | 137 | 134 | 132 | 129 | 127 | 123 | 120 | 118 | 118 | 115 | 115 | 112 | 107 | 104 | 103 | 97 | 94 | 89 | 89 | 87 | 82 | 80 | 76 | 71 | 70 | 65 | 63 | 59 | 56 | 53 | 53 | 49 | 47 | 44 | 42 | 38 | 33 | 33 | 27 | 26 | 23 | 18 | 16 | 14 | 12 | 9 | 4 | 0 | 0 | -4 | -10 | -12 | 4605
WEB IMPLEMENTATION FOR PREDICTING STORE OWNER SALES USING MACHINE LEARING AND AWS