## Sheet1
EPIC | USER STORY | PRIORITY | VALUE | RISK | ESTIMATE | DESCRIPTION | DEPENDENCIES
Requirements Gathering | Get all the research articles required for the project. | 2 Med | 1 High | 4 Low | SM | We have discovered all the articles that are useful for implementing the project. | None
Data Gathering | To download the the data set and let the data ready for training and testing. | 1 High | 1 High | 2 Med | MD | Downloaded the dataset from kaggle.com - https://www.kaggle.com/datasets/shivan118/big-mart-sales-prediction-datasets | Dataset has been downloaded from kaggle.
Data Analysis | To Perform explorartory data analysis for the downloaded dataset using feature selection. | 1 High | 1 High | 2 Med | MD | To clean the data using different techniques like feature selection. | Dataset downloaded from kaggle
Data Analysis | Data visualization and feature correlation using klib library. | 1 High | 1 High | 2 Med | MD | A user-friendly Python library designed to simplify and automate tasks in EDA. Used feature correlation matrix. | Dataset scaled
Data Cleaning | Generated "cleaned.csv" after cleaning the dataset. | 1 High | 1 High | 2 Med | MD | Cleaned the dataset using klib library. | Dataset cleaned
Machine Learning Models Implementation | List the ML Models and their dependencies which are to be implemented. | 2 Med | 2 Med | 1 High | MD | List down the models and dependencies which are implemeneted in the project. | ML models like Linear Regression, Decision Tree, Gradient Boosting and XGBoost Regressor listed to be implemented
Machine Learning Models Implementation | Linear Regression Model Implementation. | 1 High | 1 High | 1 High | LG | Built linear regresssion model using the cleaned dataset. | Data set and Jupyter notebook with all the libraries installed.
Machine Learning Models Implementation | Random Forests Model Implementation. | 1 High | 1 High | 1 High | LG | Used Random Forests Classifier to obtain all possible solutions to an issue based on constraints. In our case, not the best model to be used but we tried still. | Dataset and Jupyter notebook with all the libraries installed.
Machine Learning Models Implementation | Gradient Boosting Implementation | 1 High | 1 High | 1 High | LG | Implemented Gradient Boosting to combines multiple weak prediction models into a single ensemble | Dataset and Jupyter notebook with all the libraries installed.
Machine Learning Models Implementation | XGBoost Regressor Model Implementation. | 1 High | 1 High | 1 High | LG | Used XGBoost for an optimized version of gradient boosting | Dataset and Jupyter notebook with all the libraries installed.
Model Testing and Evaluation | To Test and Evaluate all the models that are built. | 2 Med | 1 High | 1 High | LG | Test and evaluate all models which are implemented. | Linear Regression, Decision Tree, Gradient Boosting and XGBoost Regressor
Model Testing and Evaluation | To Test the Linear regression Model and evaluate it. | 2 Med | 1 High | 2 Med | LG | It is used to calculate or predict the sales using store-specific attributes. | Linear Regression model trained in jupyter notebook.
Model Testing and Evaluation | To Test the Random Forests and evaluate it. | 2 Med | 1 High | 3 Med | LG | Random Forest will be used to create a group of many individual decision trees, which then vote on the final sales prediction, to improve accuracy. | Random Forest Model trained in jupyter notebook.
Model Testing and Evaluation | To Test the Gradient Boosting and evaluate it. | 2 Med | 1 High | 2 Med | LG | Gradient Boosting implemented to build a powerful predictive model by sequentially adding decision trees, where each new tree corrects the errors of the previous one. | Gradient Boosting Model trained in jupyter notebook.
Model Testing and Evaluation | To Test the XGBoost Regressor and evaluate it. | 2 Med | 1 High | 3 Med | LG | XGBoost (Extreme Gradient Boosting) used as a highly efficient and scalable implementation of gradient boosting, utilizing advanced regularization techniques. | XGBoost Regressor trained in jupyter notebook.
Front end App Development | To build HTML page for the index page. | 2 Med | 2 Med | 2 Med | MD | To develop a customized HTML page with form for collecting the data and predicting the result in the web. | Web page where a store owner can fill the given details and then wait for the predicted output.
Front end App Development | To devlop a HTML page for the resullt screens. | 2 Med | 2 Med | 2 Med | MD | To develpoed HTML pages for the Store Owner to know the predicted sales for a given product after all the required inputs. | HTML Pages are developed for web pages.
Front end App Development | To add CSS layouts for the page | 2 Med | 2 Med | 2 Med | MD | To add styles for the index page. | HTML pages
Front end App Development | To build a pickle file with all the pre trained ML models. | 1 High | 1 High | 1 High | MD | To build a file which stores all the pre traind Machine learning models data and prediction result. | ML models implementation
Web Server Building | To build a Flask web server and host it on the web browser. | 1 High | 1 High | 2 Med | SM | To build a flask web server using python for hosting the web page and displaying the prediction result. | Web page with ML models
Web Server Building | To Verify the interaction between Web browser and Flask development server | 1 High | 1 High | 2 Med | SM | To Verfiy the Get and Post method interactions between the Web server and browser. | Needs to open the application
Web Server Building | To verify the implementation on local machine. | 1 High | 1 High | 2 Med | MD | To Test the implementation and check whether we get the expected result or not. | ML models with flask web server.
Deployment and Analysis | To deploy the web application in AWS cloud. | 2 Med | 1 High | 1 High | LG | To deploy the Project to AWS EC2 and test the expected result. | ML models with flask web server in AWS EC2.
Deployment and Analysis | Verify whether app can be deployed and interacted using browser and Flask Server. | 1 High | 1 High | 2 Med | MD | An application has been verified and deployed using browser and flask server in our project | ML models with flask web server.
Deployment and Analysis | Verify the application is running successfully post deployment. | 1 High | 1 High | 2 Med | MD | To test Application run successfully, so that the Store Owner can correctly predict the sales of a desired product
Deployment and Analysis | Verify and analyse the output with different types of data. | 2 Med | 1 High | 2 Med | MD | We have verified with different attributes of Store Owner along with dataset